## Product backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to view personalized product recommendations | MUST HAVE | None | Nivethitha E | 3- Completed
Sprint 2 | Sprint 2 | US-02 | As a user, I want recommendations based on my past purchases and ratings | MUST HAVE | US-01 | Nivethitha E | 3- Completed
Sprint 3 | Sprint 3 | US-03 | As a user, I want to see similar product suggestions | MUST HAVE | US-02 | Nivethitha E | 3- Completed
Sprint 4 | Sprint 4 | US-04 | As a user, I want popular product recommendations when no history exists | SHOULD HAVE | US-03 | Nivethitha E | 3- Completed
Sprint 5 | Sprint 5 | US-05 | As a user, I want accurate and relevant recommendations | MUST HAVE | US-04 | Nivethitha E | 3- Completed

## Sprint backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Dataset collection and preprocessing | 2025-12-04 | 2025-12-05 | Nivethitha E | Build | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Handle cold-start problem using popularity-based logic | 2025-12-15 | 2025-12-16 | Nivethitha E | Design | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-03 | Evaluate recommendation accuracy using precision and recall | 2025-12-29 | 2025-12-30 | Nivethitha E | Unit Test | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | None | Collected user interaction and product data and reviewed dataset structure
Sprint 1 | Day 2 | Missing values and inconsistent user-product interaction data | Performed data cleaning, handling missing values and normalizing dataset
Sprint 1 | Day 3 | Difficulty in selecting an appropriate recommendation approach | Analyzed collaborative and content-based filtering and finalized both approaches.
Sprint 1 | Day 4 | Cold-start issue for new users and products | Implemented fallback logic using popular products
Sprint 1 | Day 5 | Low initial accuracy of recommendation results | Tuned model parameters and evaluated performance using precision and recall metrics

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-02-02 | 2/16/2026 | Nivethitha E | Project planning, UI wireframing, and early data profiling | Jumping into coding without understanding dataset structures | Defining product requirements clearly | Followed a structured workflow for data preprocessing and established project architecture
2 | 2 | 2/17/2026 | 2/18/2026 | Nivethitha E | Initialize Reflex frontend, setting up routing, pages, and components | Ignoring folder structures and mixing frontend/backend logic | Isolating reusable components like Navbars and Footers | Set up the foundation UI (Home, Cart, Profile, etc.)
3 | 3 | 2/19/2026 | 2/28/2026 | Nivethitha E | Implement Firebase backend authentication and database connections | Hardcoding credentials instead of using environment variables | Regularly reviewing frontend component styling | Integrated user login and signup functionality securely
4 | 4 | 29-02-2026 | 2026-10-03 | Nivethitha E | Build baseline recommender engine (Content-based & Collaborative Filtering) | Manually checking recommendations without an automated pipeline | Preprocessing CSV datasets via Pandas without warnings | Developed models to personalize the product feed
5 | 5 | 2026-11-03 | 3/22/2026 | Nivethitha E | Connect the Recommender API to Reflex State (ProductsState) dynamically | Storing massive user states redundantly in the frontend | Handling data fetching efficiently using async methods | Replaced static placeholders with dynamic AI-curated products
6 | 6 | 3/23/2026 | 3/28/2026 | Nivethitha E | Implement end-to-end shopping Cart and Order History flows | Letting bad test data reside in the DB | Testing the full user journey continuously | Built cart logic and Razorpay/Redirect simulated payment flows